## Pre-Hiatus
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | EW | Provide data on the difference between amount secured under CMP192 and actual cancellations | Proposer gave update on presentation | WG2 | Closed | WG3
2 | WG1 | EW | Provide information on the amount of connections triggering transmission works | Agreed to close as no longer necessary. Question too wide. | WG2 | Closed | WG3
3 | WG1 | EW/TC | Catch up offline regarding new works triggering Final Sums |  | WG2 | Closed | WG2
4 | WG1 | AP | Investigate potential STC changes |  | WG2 | Closed | WG2
5 | WG1 | EW | Investigate the potential for negative costs if Demand is applied to wider works |  | WG2 | Closed | WG2
6 | WG1 | EW | Provide update on interim arrangements | Proposer gave update on presentation | WG2 |  | WG3
7 | WG1 | AP | Look into definitions for attributable works for Demand and TIC |  | WG2 | Closed | WG3
8 | WG1 | EW | Provide justification for Workgroup Consultation that extending Section 15 is the correct solution | Previous action: Provide justification for Workgroup Consultation that extending Section 15 is the correct solution | WG2
9 | WG1 | AP | Provide draft legal text |  | WG2
10 | WG1 | LT | Provide Terms of Reference update to CUSC Panel |  | 45190 | Closed | WG2
11 | WG2 | AP | Provide an update of status of the term ‘Seven Year Statement’ within the CUSC
12 | WG2 | RM/AP | Provide wording in ConsAg (Construction Agreement) for key consents
13 | WG2 | RM | Provide update on implementation date for existing Users
14 | WG2 | RM | Investigate whether a guidance note can be provided for FSM
15 | WG2 | EW | Check figures provided for pre-trigger and circulate UCM guidance document to the Workgroup | Figures provided were from the current UCM guidance document
16
17

## Post-Hiatus
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 |  | Provide illustrative examples which work backwards from the energy price cap timetable to identify the latest point at which a BSUoS fixed price reset can be implemented. |  | WG2 | Open
2 | WG1 |  | Provide detail and rationale supporting percentage thresholds (the proposed 75% working capital trigger) and the four month and one week minimum notice period |  | WG2 | Open
3 | WG1 |  | Provide worked examples demonstrating possible tariff reset decisions based on the current situation if a 4 month and 1 week minimum notice period was in place, demonstrating the trade‑offs between longer (earlier/less certain) and shorter (later/more certain) notice. |  | WG2 | Open
4 | WG1 |  | Consider a possible situation in which tariffs should not be reopened or in effect for a 15 month notice period. |  | WG2 | Open